SafeGrowth Vault

Development Plan

Version 1.2  |  March 2026

Version 1.2 adds NAS hardware support across all milestones. Tags: [NEW] = added in v1.2; [NAS] = NAS-specific motivation.

Target Team: 3 developers (Glenn + 2 remote collaborators)

Development Environment: Lenovo Flex (primary), OptiPlex 990, Dell Latitude, home-built PC, Android phones, NAS test node (added v1.2)

# Revision History

| Version | Date | Author | Summary |
| --- | --- | --- | --- |
| 1.0 | 2025 | SafeGrowth Team | Initial draft |
| 1.1 | 2026-03 | SafeGrowth Team | Replace liboqs/gorocksdb/bellman with pure Go equivalents; fix PoR seed architecture; add co-bootstrap task Week 8; update risk register; bump Go min to 1.24 |
| 1.2 | 2026-03 | SafeGrowth Team | NAS hardware support: add Super Anchor tier; FreeBSD CI target; SIGTERM graceful shutdown (Week 4); mDNS interface auto-detection (Week 3); NAS install scripts to repo structure; passphrase file injection; NAS-specific risk register entries; maintenance mode task (Weeks 13-14) |

# Overview

Development is organized into three milestones aligned with three deployment phases:

- Milestone 1 — Local Testnet (Weeks 1-4): working personal backup across devices on a LAN

- Milestone 2 — Trusted Group Network (Weeks 5-10): expand to remote friends, NAT traversal, invite system

- Milestone 3 — Open Participation (Weeks 11-20): Sybil resistance, PoR, reputation, full trustless operation

# Repository Structure

Updated for v1.2 — NAS install scripts added to scripts/install/:

safegrowth/

├── node/                    # Node daemon (Go)

│   ├── cmd/main.go

│   ├── identity/

│   ├── storage/             # Shard storage engine (Pebble)

│   ├── crypto/

│   ├── sharding/

│   ├── gossip/

│   ├── consensus/

│   ├── por/

│   ├── reputation/

│   ├── credits/

│   ├── replication/

│   ├── api/

│   └── config/

├── cli/

├── app/                     # Flutter client

├── scripts/

│   ├── backup-linux.sh

│   ├── backup-windows.ps1

│   └── install/

│       ├── install-linux.sh

│       ├── install-windows.ps1

│       ├── install-synology.sh    # [NEW][NAS] DSM 7.x

│       ├── install-qnap.sh         # [NEW][NAS] QTS 5.x

│       ├── install-truenas-scale.sh # [NEW][NAS] TrueNAS SCALE

│       ├── install-truenas-jail.sh  # [NEW][NAS] TrueNAS CORE / FreeBSD jail

│       └── install-unraid.sh        # [NEW][NAS] Unraid

├── docs/

└── .github/workflows/build.yml

# Milestone 1: Local Testnet (Weeks 1-4)

Goal: Personal backup working across OptiPlex, Dell Latitude, Lenovo Flex, and Android phones on home LAN.

## Week 1: Identity and Storage Foundation

- Initialize Git repository; set up Go module

- Implement identity package

  - Generate ML-DSA-65 keypair using github.com/trailofbits/ml-dsa/mldsa65 on first run

  - Generate ML-KEM-768 keypair using crypto/mlkem (Go stdlib >= 1.24) on first run

  - Persist both keypairs to ~/.safegrowth/identity encrypted with AES-256-GCM + Argon2id passphrase

  - Expose NodeID() -> stable string derived from ML-DSA public key hash

  - Support SGV_IDENTITY_PASSPHRASE_FILE env var for headless/NAS deployments (reads passphrase from file path, not inline value) [NEW] [NAS]

- Implement storage package (Pebble) with PutShard, GetShard, DeleteShard, HasShard

- Implement REST API: GET /status, POST /shards, GET /shards/{id}

- Write unit tests for identity and storage

## Week 2: Encryption and Sharding

- Implement crypto package (AES-256-GCM, ML-KEM, ML-DSA, SHA3, BLAKE3, Argon2id, HKDF)

- Implement sharding package using klauspost/reedsolomon (2-of-3 default)

- Integrate encryption into storage: PutShard encrypts before writing

- Write unit tests: encrypt->shard->reconstruct->decrypt round-trip

## Week 3: mDNS Discovery and Peer Replication

- Add go-libp2p dependency; implement gossip/mdns.go

  - Announce node ID + IP:port via mDNS every 30 seconds

  - mDNS binding MUST auto-detect the interface with the default route; automatically exclude Docker bridge interfaces (docker0, br-*) [NAS]

  - Discover peer announcements; add to peer table; persist to peers.json

- Implement basic replication (push shard to all known peers on store)

- Test on real LAN: run daemon on OptiPlex and Lenovo Flex simultaneously

## Week 4: CLI, Linux Backup Integration, Cross-Compile

- Implement full CLI (cobra): node start/stop/status, network status, backup, restore

- Linux backup integration: inotify watcher, systemd service unit file, install-linux.sh

- Implement SIGTERM graceful shutdown handler [NEW] [NAS]

  - On SIGTERM: flush Pebble WAL, complete in-flight shard transfers, gossip offline announcement [NEW] [NAS]

  - All within 30 seconds of SIGTERM receipt [NEW] [NAS]

  - Critical on NAS where OS updates trigger unannounced reboots [NAS]

- Cross-compile for all targets:

CGO_ENABLED=0 GOOS=linux   GOARCH=amd64 go build -o dist/safegrowth-node ./node/cmd

CGO_ENABLED=0 GOOS=windows GOARCH=amd64 go build -o dist/safegrowth-node.exe ./node/cmd

CGO_ENABLED=0 GOOS=linux   GOARCH=arm64 go build -o dist/safegrowth-node-arm64 ./node/cmd

CGO_ENABLED=0 GOOS=android GOARCH=arm64 go build -o dist/safegrowth-node-android ./node/cmd

CGO_ENABLED=0 GOOS=freebsd GOARCH=amd64 go build -o dist/safegrowth-node-freebsd ./node/cmd  # [NEW][NAS] TrueNAS CORE

- Verify all five binaries run on target hardware [NEW]

- Set up GitHub Actions CI: build all five targets on every push to main [NEW] [NAS]

# Milestone 2: Trusted Group Network (Weeks 5-10)

Goal: Two remote friends can join the network. NAT traversal works. All connections authenticated. Credits begin accruing.

## Week 5: Mutual TLS and Signed Gossip

- Upgrade all peer connections to mutual TLS

- Add message signing to gossip layer (ML-DSA-65)

- Define protobuf schemas for all gossip message types including MAINTENANCE_WINDOW [NAS]

- Unit test: tampered gossip message rejected; valid message processed

## Week 6: Invite System

- Implement invite token generation and validation (base58, single-use, 24h default expiry)

- Implement join flow: keypair generation, join request signing, peer list exchange

- CLI: safegrowth-cli invite generate --expires 24h / safegrowth-cli join ...

## Week 7: NAT Traversal and DDNS

- Set up DuckDNS for OptiPlex anchor; cron job to update every 5 minutes

- Implement UDP hole punching via libp2p built-in hole punching

- Implement relay node functionality (E2EE preserved; relay sees only ciphertext)

- Test: Friend 1 joins from different home network

## Week 8: Bootstrap Peer Discovery and Phase 2 Replication

- Implement bootstrap peer config (minimum 2 entries, per PD-06/NF-08)

- Immediately set up Friend 1's anchor node as co-bootstrap after join

- Upgrade erasure coding to 3-of-5 for internet-connected nodes

- Upgrade replication manager to reputation-aware placement (basic uptime score)

- NAS operator co-bootstrap note: if a NAS node is the sole anchor, the operator MUST recruit a second anchor before Phase 2; the install-synology.sh/install-truenas-*.sh scripts will surface this requirement during setup [NAS]

## Week 9: Credit System

- Implement credit ledger (Pebble, append-only, credits/ key prefix)

- Credit accrual rates: +1/GB/month storage, +0.75/hr Super Anchor, +0.5/hr Anchor, +0.25/hr Mid [NAS]

- Implement lightweight consensus for credit validation (3-node quorum)

- CLI: safegrowth-cli credits balance / history

## Week 10: Windows, Android, Integration Testing

- Windows backup: PowerShell FileSystemWatcher, NSSM service

- Android background service (Flutter)

- End-to-end integration test: all nodes online including any NAS test node [NAS]

# Milestone 3: Open Participation (Weeks 11-20)

## Weeks 11-12: Sybil Resistance

- Implement resource proof challenge on join (256MB dataset, 60-second window)

- Implement reputation probation period (72 hours; zero credits; no primary placement)

- Add computational PoW puzzle to join flow

## Weeks 13-14: Proof of Retrievability

- Implement PoR challenge seed establishment (ML-KEM key exchange, 3+ verifying peers)

- Implement PoR challenge issuance and response

- Implement maintenance mode gossip item (MAINTENANCE_WINDOW type) [NEW] [NAS]

  - Node broadcasts signed maintenance window announcement with start/end timestamps [NEW] [NAS]

  - Rate-limited to 2 declarations per 7-day period per node [NEW] [NAS]

  - Verifiers suppress PoR failure reputation penalty during declared window [NEW] [NAS]

  - CLI: safegrowth-cli node maintenance --start --duration 4h --reason 'RAID rebuild' [NEW] [NAS]

- Reputation impact: 3 consecutive failures (outside maintenance window) -> shard migration [NAS]

- Test: delete shard; verify PoR detects and triggers re-replication

- Test: trigger RAID rebuild on NAS test node; declare maintenance window; verify no reputation penalty [NAS]

## Weeks 15-16: ZK-PoR and Full Byzantine Consensus

- Integrate github.com/consensys/gnark (pure Go, zero CGO)

- Benchmark gate FIRST: measure Groth16 prove time on OptiPlex 990 (target <= 2s) and Pi 3B (target <= 10s)

- Benchmark NAS Super Anchor hardware as well to establish expected proof times [NEW] [NAS]

- Implement ZK-PoR circuit and upgrade consensus to full PBFT-lite (5-7 node quorums)

## Weeks 17-18: Full Reputation System and Adaptive Replication

- Implement composite reputation score: uptime_ratio x 0.4 + por_pass_rate x 0.4 + latency_score x 0.2

- Implement Super Anchor tier derivation: sustained PoR pass rate + uptime + storage_type capability hint [NEW] [NAS]

- Quarantine: nodes below 0.6 receive no new placements

- Adaptive replication: prefer Super Anchor and Anchor nodes for primary shard placement [NAS]

## Weeks 19-20: Flutter App, DHT, Phase 3 Testing

- Complete Flutter app (QR onboarding, file manager, node dashboard, geo-diversity map, gamified badges)

- Implement DHT-based peer discovery (libp2p Kademlia)

- Upgrade erasure coding to 5-of-9

- Full Phase 3 integration test including NAS node participation [NAS]

# CI Pipeline

GitHub Actions (.github/workflows/build.yml) — all five targets required on every PR:

on: [push, pull_request]

jobs:

build:

runs-on: ubuntu-latest

steps:

- go test ./...

- CGO_ENABLED=0 GOOS=linux   GOARCH=amd64 go build ./node/cmd

- CGO_ENABLED=0 GOOS=windows GOARCH=amd64 go build ./node/cmd

- CGO_ENABLED=0 GOOS=linux   GOARCH=arm64 go build ./node/cmd

- CGO_ENABLED=0 GOOS=android GOARCH=arm64 go build ./node/cmd

- CGO_ENABLED=0 GOOS=freebsd GOARCH=amd64 go build ./node/cmd  # [NEW][NAS] TrueNAS CORE

- Upload artifacts (all five binaries)

CGO_ENABLED=0 is enforced on every target. No C toolchain is installed on the CI runner. Any PR introducing a CGO dependency fails at this step.

# Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| trailofbits/ml-dsa API changes | Low | Low | Pin to specific tagged version in go.mod; review changelog before upgrading |
| gnark proof generation exceeds 2s on OptiPlex 990 | Medium | Medium | Benchmark gate at Week 15; fallback: PLONK backend, proof batching, or defer ZK-PoR to post-MVP |
| QUIC hole punching fails for friend's NAT | Low | Medium | Relay fallback already designed; test early Week 7 |
| Android background service killed by battery optimization | High | Medium | Document workaround; use termux-wake-lock; Flutter background service has known workarounds |
| Reed-Solomon reconstruction fails with corrupted shards | Low | High | Test extensively in Week 2; include checksum validation before reconstruction |
| Gossip storm on large network | Low | Medium | Version vectors and bandwidth caps prevent this; test with simulated 50-node network in M3 |
| [NAS] RAID rebuild causes extended PoR timeout failures | Medium | Medium | Mitigated by maintenance mode (ST-08, Weeks 13-14); operator declares maintenance window before/during RAID rebuild; PoR failures during window do not count toward reputation streak |
| [NAS] Automated NAS OS snapshots create inconsistent Pebble state if taken mid-write | Low | High | Install scripts document exclusion of SafeGrowth data directory from automated snapshots; NAS install guide includes explicit warning |
| [NAS] BBU write cache may cause fsync() durability assumptions to fail | Low | High | Install scripts recommend write-through cache mode for SafeGrowth data volume; documented in NAS install guides and runbook |
| [NAS] Docker bridge mDNS announcement captured on wrong interface | Medium | Medium | mDNS implementation must auto-detect default-route interface and exclude docker0/br-* (Week 3); verified in NAS integration test |
| [NAS] NAS clock drift causes E-005 timestamp rejections and silent peer isolation | Medium | Medium | NF-19 startup NTP check; clock drift warning logged when delta approaches 25s threshold; NAS install checklist includes NTP verification |

# Milestone Summary

| Milestone | Weeks | Deliverable | Trust Model |
| --- | --- | --- | --- |
| 1 - Local Testnet | 1-4 | Personal backup on LAN, all platforms including FreeBSD binary | Fully trusted (personal devices) |
| 2 - Trusted Group | 5-10 | Remote friends, NAT traversal, credits, NAS operator support | Web of trust via invite chain |
| 3 - Open Network | 11-20 | Any hardware including NAS, PoR with maintenance mode, Super Anchor tier, reputation, Sybil resistance | Zero trust; math-enforced |